## Snag tracker
SAMPLE TRACKER: sample data, not a real inspection
Snag tracker · 12 Sample Close, Exampletown, AB1 2CD · Inspected 27/09/2026 · Sample Surveyor, Sample Surveying Ltd
No. | Room | Location | Description | Category | Severity | Status | Due date | Assigned to | Reference | Created | Reviewed by | Photos
1 | Kitchen | Worktop by sink | Incomplete worktop sealant | Finish | Minor | New |  | Site manager |  | 27/09/2026 |  | 1
2 | Bathroom | Above door frame | Hairline crack above the door frame | Finish | Minor | New |  | Site manager |  | 27/09/2026 |  | 0
3 | External Elevation | By stone sill | Mortar discrepancy by the stone sill | Finish | Moderate | New |  | Site manager |  | 27/09/2026 |  | 1
4 | Understairs Cupboard |  | Poor plaster and decorative finish | Finish | Moderate | New |  | Site manager |  | 27/09/2026 |  | 1
5 | External Elevation | Patio door | Gaps in mastic under the patio door sill | Finish | Moderate | New |  | Site manager |  | 27/09/2026 |  | 1
6 | Garage | Garage door | Missing fixings to garage door bracket | Missing | Moderate | New |  | Site manager |  | 27/09/2026 |  | 1
7 | Kitchen | Under sink | Leaking waste pipe under the kitchen sink | Function | Major | New |  | Site manager |  | 27/09/2026 |  | 1
8 | Cylinder Cupboard |  | Missing decorative finish to wall | Finish | Moderate | New |  | Site manager |  | 27/09/2026 |  | 1